## BACKLOG
| CATEGORY | ACTIVITY | ESTIMATED HOURS | RESPONSIBLE | Together | CHECK | Status | Comment
THIS SPRINT (1 - ENDS 2018-04-30) | Grafik | Bakgrund sprite (1a simpel version) | 0.5 | Sally |  | Uploaded to dropbox and checked by team | Finished
| Grafik | Vägg sprite (1a simpel version) | 0.5 | Sally |  | Uploaded to dropbox and checked by team | Finished
| Grafik | Plattform stor (1a simpel version) | 0.5 | Sally |  | Uploaded to dropbox and checked by team | Finished
| Grafik | Plattform liten 3 delar H/M/V (1a simpel version) | 0.5 | Sally |  | Uploaded to dropbox and checked by team | Finished
| Grafik | Player Vänster (1a simpel version) | 0.5 | Sally |  | Uploaded to dropbox and checked by team | Finished
| Grafik | Player Höger (1a simpel version) | 0.016667 | Sally |  | Uploaded to dropbox and checked by team | Finished
| Grafik | Hoppa Vänster (1a simpel version) | 0.5 | Sally |  | Uploaded to dropbox and checked by team | Finished
| Grafik | Hoppa Höger (1a simpel version) | 0.016667 | Sally |  | Uploaded to dropbox and checked by team | Finished
| Grafik | Hoppa högt vänster (1a simpel version) | 0.5 | Sally |  | Uploaded to dropbox and checked by team | Finished
| Grafik | Hoppa högt höger (1a simpel version) | 0.016667 | Sally |  | Uploaded to dropbox and checked by team | Finished
| Programmering | GameControls (Rolling background & Platform mover) | 0.5 | Stefan |  | Uploaded to dropbox and checked by team | Finished
| Programmering | GameControls (PlatformInitiater) | 2 | Henrik |  | Uploaded to dropbox and checked by team | Finished
| Programmering | GameControls (Score, Move background if too high, death (falls out of screen)) | 2 | Stefan |  | Uploaded to dropbox and checked by team | Finished
| Programmering | PlayerControls (Move, Jump, Gravity) | 2 | Sebbe |  | Uploaded to dropbox and checked by team | Finished
| Programmering | Bottom Shredder (Garbage Collector) | 0.25 | Sebbe |  | Uploaded to dropbox and checked by team | Finished
| Scene | Collect into Scene | 4 | Henrik | x |  | Finished
| UI | Canvas (Level) | 0.33333 | Henrik | x |  | Finished
| UI | Canvas (Score, Level, Timer) | 0.33333 | Henrik | x |  | Ongoing
| UI | StartMenu | 0.33333 | Henrik | x |  | Finished
| Programmering | Setup GIT(HUB) | 1 | Henrik |  |  | Ongoing
| Programmering | Clean code | 4 | Sebbe | x |  | Ongoing
| Programmering | Technical meeting | 3 | Stefan | x |  | Ongoing | Set Sunday evening
| Grafik | Snygga till sprites | 3 | Sally |  |  | Ongoing
| Grafik | Skrollbar bakgrund | 0.5 | Stefan |  |  | Ongoing
BACKLOG
| Programmering | Extra lives
| Programmering | If Extra lives - save progress...
Data validation
Grafik
UI
Programmering
Scene
Status
Ongoing
Finished

## INFO
Sum of ESTIMATED HOURS | Column Labels
Row Labels | x | (blank) | Grand Total
Henrik | 5 | 2 | 7
Sally |  | 3.55 | 3.55
Sebbe |  | 2.25 | 2.25
Stefan |  | 2.5 | 2.5
(blank)
Grand Total | 5 | 10.3 | 15.3